## Project Budget
Budget: Project Plant Pals Operations & Training
[7 empty] | TARGET BUDGET | ACTUAL/ FINAL SPEND | UNDER/ OVER
[7 empty] | 3600 | 0 | 3600
| LABOR |  |  | MATERIALS |  | FIXED COST | BUDGET | ACTUAL | UNDER/OVER
MILESTONES & TASKS | EMPLOYEE DETAILS | HOURS | RATE | UNITS | $/UNIT
Milestone 1: Establish a plant delivery and logistics plan
Task 1: Purchase delivery trucks |  |  |  | 2 | 1000 | 2000 | 2000 | 2000 | 0
Task 2:Develop logistics plan | Jane Doe | 10 | 50 |  |  |  | 500 | 500 | 0
Task 3:Train delivery personnel | John Smith | 20 | 50 |  |  |  | 1000 | 1000 | 0
-- | [5 empty] | Total | 3500 | 3500
Milestone 2:Set up distribution channels
Task 1: Negotiate with suppliers | Emily Davis | 10 | 50 |  |  |  | 500 | 500 | 0
-- | [5 empty] | Total | 500 | 500
Milestone 3:Launch marketing campaign
Task 1: Design marketing materials | Graphic Designer | 15 | 60 |  |  |  | 900 | 900 | 0
Task 2: Social media ads |  |  |  | 10 | 50 |  | 500 | 500 | 0
Task 3: Local event | Event Coordinator | 10 | 50 |  |  |  | 500 | 500 | 0
-- | [5 empty] | Total | 1900 | 1000
Reserve buffer | [6 empty] | 3600
TOTAL | [6 empty] | 3600 | 5900 | -2300