## Status Report
Project Name: Plant Pals Operations
Today's date: July 5
Summary |  |  |  | Overall Status (RAG)
We have installed new software to keep track of incoming orders and begun sending out the first test batch of Plant Pals to customers. However, we have run into issues with product quality, customer communication, and the delivery process. Our next milestones include sending the test batch customers newsletters on plant upkeep and sending out the second batch of plants. This report also includes top risks and issues that have arisen and how we intend to take action. |  |  |  | Red
Completed Tasks and Milestones
Description | Date | Status | Owner |  | Comments
Installed new software to track incoming orders | June 5 | Completed | IT Specialist |  | Software is now operational and stable.
Began sending test batches of Plant Pals orders to customers | June 21 | Completed | Fulfillment Team |  | The number of orders exceeded targets by 15%.
Upcoming Tasks and Milestones
Description | Date | Status | Owner |  | Comments
Send the first batch customers e-newsletters on how to take care of their plants. | July 19 | Upcoming | Fulfillment Director |  | The newsletter must follow Office Green’s brand design guidelines.
Send out the second batch of Plant Pals to customers | July 19 | Upcoming | Fulfillment Director |  | Ensure all quality checks are completed before dispatch.
Top Risks and Issues
Issue |  | Impact | Action |  |  | Owner
Product quality, customer communication, and delivery process issues |  | Profit loss, complaints, and budget issues | Hire and train more delivery drivers |  |  | Warehouse Operations Manager
The customer relations team is receiving only 30% of requests and complaints |  | Customer dissatisfaction | Fix problems with new customer service software
Insufficient customer service representatives |  | Customer requests and complaints not being addressed in a timely manner | Hire and train more delivery drivers |  |  | HR Specialist